## GanttChart
Final Project: schedule, wbs, and Gantt
Andrea Baccolini: x18147518@student.ncirl.ie
| Project Start Date | 2019-05-25 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12
| Project Lead | AndreaB | [6 empty] | 2019-05-20 | [6 empty] | 2019-05-27 | [6 empty] | 2019-06-03 | [6 empty] | 2019-06-10 | [6 empty] | 2019-06-17 | [6 empty] | 2019-06-24 | [6 empty] | 2019-07-01 | [6 empty] | 2019-07-08 | [6 empty] | 2019-07-15 | [6 empty] | 2019-07-22 | [6 empty] | 2019-07-29 | [6 empty] | 2019-08-05
 | time axis 2019-05-20 to 2019-08-11
WBS | TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2019-05-20 to 2019-08-11
1 | Project Setup |  |  |  | - |  |  | -
1.1 | Declaration cover sheet |  |  | 2019-05-25 | 2019-05-26 | 2 | 100% | 0
1.2 | Project Proposal creation and submission |  |  | 2019-05-27 | 2019-06-03 | 8 | 0% | 6
1.3 | Ethics approval document |  |  | 2019-05-27 | 2019-06-03 | 8 | 0% | 6
1.4 | Project requirement specs document |  |  | 2019-05-27 | 2019-06-14 | 19 | 0% | 15
1.4.1 | Project requirement specs submission |  |  | 2019-06-15 | 2019-06-15 | 1 | 0% | 0
1.4.2 | Project Analysis and Design documentation |  |  | 2019-06-16 | 2019-07-12 | 27 | 0% | 20
1.5 | Project Analysis and Design documentation submission |  |  | 2019-07-13 | 2019-07-13 | 1 | 0% | 0
1.6 | Development environment setup |  |  | 2019-06-22 | 2019-06-28 | 7 | 0% | 5
1.6.1 | Prototyping |  |  | 2019-06-22 | 2019-06-28 | 7 | 0% | 5
2 | Sprint 1 |  |  |  | - |  |  | -
2.1 | Interim Progress Report: subsmission |  |  | 2019-06-29 | 2019-06-29 | 1 | 0% | 0
2.2 | Development start |  |  | 2019-06-28 | 2019-07-11 | 14 | 0% | 10
2.2.1 | Development of server side |  |  | 2019-06-28 | 2019-07-04 | 7 | 0% | 5
2.2.2 | db connection and data CRUD |  |  | 2019-07-03 | 2019-07-10 | 8 | 0% | 6
2.3 | Second project check |  |  | 2019-07-11 | 2019-07-11 | 1 | 0% | 1
3 | Sprint 2 |  |  |  | - |  |  | -
3.1 | Client side development start |  |  | 2019-07-12 | 2019-07-17 | 6 | 0% | 4
3.2 | Periodical documentation update, including: project plan, design document, testing document, final project report |  |  | 2019-07-17 | 2019-07-26 | 10 | 0% | 8
3.3 | Third project check |  |  | 2019-07-22 | 2019-07-22 | 1 | 0% | 1
3.4 | Development of final functionalities and tuning |  |  | 2019-07-23 | 2019-07-29 | 7 | 0% | 5
3.5 | Testing of the webapp |  |  | 2019-07-29 | 2019-08-02 | 5 | 0% | 5
4 | Sprint 3 |  |  |  | - |  |  | -
4.1 | Video and project presentation creation and submission |  |  | 2019-07-30 | 2019-07-31 | 2 | 0% | 2
4.2 | Wrap up of code and submission |  |  | 2019-08-04 | 2019-08-04 | 1 | 0% | 0
4.3 | Project final report submission [including declaration cover sheet] |  |  | 2019-08-04 | 2019-08-05 | 2 | 0% | 1
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.